## Lookups
Trade | Issue_Type | Status | Relation | Handover_Type | Resource_Type
GC | 设计 | Open | FS | 结构 | 吊篮
幕墙 | 材料 | In-Progress | SS | 砌筑 | 塔吊
门窗 | 场地 | Closed | FF | 抹灰 | 气吊
机电 | 移交 |  | SF | 屋面 | 班组
精装 | 验收 |  |  | 立面
天气

## Master_Plan
WBS_ID | Node_Name | Building | Floor | Trade | Planned_Start | Planned_Finish | Duration_d | Crew_Size | Preconditions | Accept_Criteria | Milestone_Flag | Total_Float_d | RAG
B01-F-EXT-001 | 外墙抹灰完成 | B01 | ALL | GC | 2025-08-01 | 2025-08-05 | 5 | 12 |  | 检验批合格 | N | 1 | Yellow
B01-F-EXT-002 | 外墙第一遍腻子 | B01 | ALL | GC | 2025-08-06 | 2025-08-08 | 3 | 10 |  | 检验批合格 | N | 1 | Yellow
B01-F-EXT-003 | 拆外架 | B01 | ALL | GC | 2025-08-09 | 2025-08-10 | 2 | 8 | 外墙抹灰+一遍腻子完成 | 安全验收通过 | N | 1 | Yellow
B01-RF-001 | 屋面保护层浇筑完成 | B01 | RF | GC | 2025-08-01 | 2025-08-05 | 5 | 8 |  | 检验批合格 | N | 5 | Green
B01-RF-002 | 屋面保护层养护达标(≥10d) | B01 | RF | GC | 2025-08-05 | 2025-08-15 | 11 | 0 | 屋面保护层完成 | 养护记录合格 | Y | 3 | Green
B01-GONDL-001 | 吊篮安装 | B01 | ALL | 幕墙 | 2025-08-16 | 2025-08-16 | 1 | 6 | 外架拆除完成+屋面养护≥10天 | 设备验收合格 | N | 2 | Green
B01-PAINT-001 | 外立面涂料开始 | B01 | ALL | GC | 2025-08-17 | 2025-08-25 | 9 | 10 | 吊篮到位 | 抽检合格 | N | 0 | Yellow
B01-GLASS-001 | 玻璃/石材/铝板安装开始 | B01 | ALL | 幕墙 | 2025-08-17 | 2025-08-30 | 14 | 12 | 吊篮到位 | 抽检合格 | N | 0 | Yellow
B01-SEAL-001 | 打胶密封 | B01 | ALL | 幕墙 | 2025-08-31 | 2025-09-03 | 4 | 6 | 立面安装完成 | 淋水试验合格 | N | 0 | Yellow
B01-HANDOVER-001 | 成品保护与清理+分段验收 | B01 | ALL | 幕墙 | 2025-09-04 | 2025-09-06 | 3 | 6 |  | 验收合格 | Y | 0 | Yellow

## Actuals
WBS_ID | Report_Date | Actual_Start | Actual_Finish | %Complete | Daily_Quantity | Cum_Quantity | Blockers | PIC
B01-F-EXT-001 | 2025-08-07 | 2025-08-01 | 2025-08-07 | 100 |  |  |  | 张三
B01-F-EXT-002 | 2025-08-11 | 2025-08-09 | 2025-08-11 | 100 |  |  |  | 张三
B01-F-EXT-003 | 2025-08-12 | 2025-08-11 | 2025-08-12 | 100 |  |  |  | 李四
B01-RF-001 | 2025-08-05 | 2025-08-01 | 2025-08-05 | 100 |  |  |  | 王五
B01-RF-002 | 2025-08-15 | 2025-08-05 | 2025-08-15 | 100 |  |  |  | 王五
B01-GONDL-001 | 2025-08-16 | 2025-08-16 |  | 5 |  |  |  | 赵六

## Dependencies
Pre_WBS_ID | Succ_WBS_ID | Relation | Lag_d
B01-F-EXT-002 | B01-F-EXT-003 | FS | 0
B01-RF-002 | B01-GONDL-001 | FS | 0
B01-F-EXT-003 | B01-GONDL-001 | FS | 0
B01-GONDL-001 | B01-PAINT-001 | FS | 0
B01-GONDL-001 | B01-GLASS-001 | FS | 0
B01-GLASS-001 | B01-SEAL-001 | FS | 0
B01-SEAL-001 | B01-HANDOVER-001 | FS | 0

## Thresholds
Trade | RAG_SPI_Green | RAG_SPI_Yellow | Float_Green_d | Float_Yellow_d | Lookahead_Weeks
GC | 0.95 | 0.85 | 3 | 2 | 4
幕墙 | 0.95 | 0.85 | 3 | 2 | 4
门窗 | 0.95 | 0.85 | 3 | 2 | 4
机电 | 0.95 | 0.85 | 3 | 2 | 4
精装 | 0.95 | 0.85 | 3 | 2 | 4

## Issues_Log
Issue_ID | Date | WBS_ID | Building | Issue_Type | Description | Owner | Due_Date | Status | Attachment
ISS-0001 | 2025-08-10 | B01-F-EXT-003 | B01 | 场地 | 外架拆除工序与内装交叉，需夜间施工 | 总包-现场经理 | 2025-08-12 | In-Progress

## Handovers
From_Trade | To_Trade | Building | Area/Axis | Handover_Type | Planned_Date | Actual_Date | Accept_Result
GC | 幕墙 | B01 | A~C/1~4轴 | 立面 | 2025-08-16 | 2025-08-16 | 合格

## Resources
Resource_Type | Qty | Location | Booking_Slot | Owner | Conflicts
吊篮 | 6 | B01 东立面 | 2025-08-16 ~ 2025-09-10 | 幕墙-设备主管 | 与B02冲突(建议错峰)

## Dashboard
Week_Start | 2025-08-11
Week_End | 2025-08-17
PCR (Project)
ACR (Project)
SPI (Project)
Project RAG (by SPI)
Trade | PCR | ACR | SPI
GC
幕墙
门窗
机电
精装

## README
使用说明： 1) 先在 Lookups 维护下拉枚举（如 Trade/Issue_Type 等）。 2) 在 Master_Plan 维护基线计划；Total_Float_d 可由CPM计算后回填。 3) 在 Actuals 每日填报，最终完成时填写 Actual_Finish。 4) Dependencies 维护工序逻辑与时差（Lag_d）。 5) Thresholds 可按专业设置 RAG 阈值。 6) Dashboard 输入周起止日，自动计算 PCR/ACR/SPI（项目/专业）。 7) Master_Plan 的 RAG 目前按文本标记；后续可由计算层自动写回。